## Resolved CM55 Bugs
ID | Title | Assigned To | Resolved Date | P | time axis 2008-08-18 to 2008-11-14
6596 | [54legacy][WX]uncheck all in AX Admin/security then check all again , WX login still failed | Li, Yue | 2008-08-14 18:13 | 1 | 2008-08-18: Be blocked by 6742; 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6341 | [WX] check componet get an error | Li, Yue | 2008-08-14 16:11 | 2 | 2008-08-18: Be blocked by 6742; 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6552 | [WX] Query Options drop down list should be disable or in readonly mode. | Liu, Travis | 2008-08-12 15:22 | 2 | 2008-08-18: Be blocked by 6742; 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6326 | [Index Server] Index Server cannot be launched correctly. | Liu, Travis | 2008-08-14 15:30 | 1 | 2008-08-18: X; 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6612 | [AX] Cannot display annotation properties window. | Liu, Travis | 2008-08-14 11:29 | 1 | 2008-08-18: X; 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6616 | [IndexServer]Full Text Search using Verity K2 Index Server doesn't work | Teng, Kevin | 2008-08-14 14:58 | 2 | 2008-08-18: X; 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: X; 2008-08-29: X; 2008-09-01: O
6618 | [AX]Fuzzing search for Chinese character doesn't work | Teng, Kevin | 2008-08-12 18:00 | 2 | bar: 2008-08-18 to 2008-08-19
6669 | ODMA Keywords and Comment textboxes length should be defined | Teng, Kevin | 2008-08-13 10:41 | 3 | bar: 2008-08-18 to 2008-08-19
6742 | Cannot login to WX. | Liu, Travis | 2008-08-18 16:00 | 1 | 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6554 | [54 Legacy][ODMA]Ctrl+A should be work in all textboxes | Teng, Kevin | 2008-08-18 11:24 | 3 | 2008-08-19: X; 2008-08-20: X(Waiting for new build); 2008-08-21: O
6742 | Cannot login to WX. | Liu, Travis | 2008-08-18 16:00 | 1 | 2008-08-20: X(Waiting for new build); 2008-08-21: X; 2008-08-22: O
6803 | Verity k2 full text search log is empty | Teng, Kevin |  | 2 | 2008-08-20: X(Waiting for new build); 2008-08-21: O
6775 | Keywords' length in Property window is different with in ODMA window | Teng, Kevin | 2008-08-19 16:12 | 3 | 2008-08-20: X(Waiting for new build); 2008-08-21: O
6776 | Remove in setup.exe doesn't work | Teng, Kevin | 2008-08-19 17:08 | 2 | 2008-08-20: X(Waiting for new build); 2008-08-21: O
6689 | Log window is not wide enough to contain all the logs | Teng, Kevin | 2008-08-19 17:33 | 3 | 2008-08-20: X(Waiting for new build); 2008-08-21: O
6529 | [Index Server]First time Start Index Server will cause "Switch to..." dialogue popup | Teng, Kevin | 2008-08-19 17:44 | 2 | 2008-08-20: X(Waiting for new build); 2008-08-21: O
6590 | [WX]endorsement print,set up 100 chinese characters,but only 53 Chinese characters are printed | Li, Yue | 2008-08-20 17:41 | 2 | bar: 2008-08-21 to 2008-08-26
6560 | [WX] Component version is not correct. | Liu, Travis | 2008-08-20 12:03 | 3 | bar: 2008-08-21 to 2008-08-22
6377 | [AX/WX/imagecapture]login failed via EVALUATION license | Li, Yue | 2008-08-21 12:02 | 2 | bar: 2008-08-22 to 2008-08-25
6489 | [Admin]Missing "e" of "Non-Unicode" | Teng, Kevin | 2008-08-21 17:23 | 3 | bar: 2008-08-25 to 2008-08-27
6689 | Log window is not wide enough to contain all the logs | Teng, Kevin | 2008-08-21 15:43 | 3 | bar: 2008-08-22 to 2008-08-29
6827 | Config window should popup first if havn't configured Index Server | Teng, Kevin | 2008-08-21 15:53 | 2 | bar: 2008-08-25 to 2008-08-27
6326 | [Index Server] Index Server cannot be launched correctly. | Liu, Travis | 2008-08-14 15:30 | 1 | bar: 2008-08-25 to 2008-08-27
6607 | [MigWizard]The icon of migration done dialogue box is not suitable | Teng, Kevin | 2008-08-22 16:37 | 3 | bar: 2008-08-25 to 2008-08-27
6718 | [54 Legacy]PDF file couldn't be OCRed | Teng, Kevin | 2008-08-22 14:38 | 2 | bar: 2008-08-25 to 2008-08-27
6297 | The starting logo is ugly | Teng, Kevin | 2008-08-25 16:04 | 2 | bar: 2008-08-26 to 2008-08-27
6495 | [54 Legacy][AX] AX will crash if import a specified file | Teng, Kevin | 2008-08-26 15:52 | 3 | bar: 2008-08-27 to 2008-08-29
6803 | Verity k2 full text search log is empty | Teng, Kevin | 2008-08-27 09:10 | 2 | bar: 2008-08-27 to 2008-09-01
6910 | [54 Legacy]App and Ver are not translated | Teng, Kevin | 2008-08-26 15:05 | 2 | bar: 2008-08-27 to 2008-08-29
6855 | [54 Legacy]Apply button should be enable if change Verity K2 Server Name | Teng, Kevin | 2008-08-26 19:55 | 3 | bar: 2008-08-27 to 2008-08-29
6856 | [54 Legacy]Server Port will be empty if change Verity K2 Server Name | Teng, Kevin | 2008-08-26 19:55 | 3 | bar: 2008-08-27 to 2008-08-29
6858 | [54 Legacy]Should not always check validation when add 1 character in App Desc | Teng, Kevin | 2008-08-26 19:55 | 3 | bar: 2008-08-27 to 2008-08-29
6918 | Switch to log will cause Index Server crash | Teng, Kevin | 2008-08-26 16:21 | 1 | bar: 2008-08-27 to 2008-08-29
6341 | [WX] check componet get an error | Li, Yue | 2008-08-27 16:02 | 2 | bar: 2008-08-28 to 2008-08-29
6440 | [Document Manager]datasource uses license server group but license info shows is not correct | Li, Yue | 2008-08-28 01:53 | 2 | bar: 2008-08-28 to 2008-08-29
6803 | Verity k2 full text search log is empty | Teng, Kevin | 2008-08-27 09:10 | 2 | bar: 2008-08-28 to 2008-09-01
6890 | [54 Legacy]CAQ behaviors in AX and WX are not consistent | Teng, Kevin | 2008-08-27 17:35 | 2 | bar: 2008-08-28 to 2008-09-08
6910 | [54 Legacy]App and Ver are not translated | Teng, Kevin | 2008-08-26 15:05 | 2 | bar: 2008-08-28 to 2008-08-29
6946 | It will cause an error when launch Admin | Teng, Kevin | 2008-08-27 12:01 | 2 | bar: 2008-08-28 to 2008-08-29
6587 | [WX]Automatically open document if query yields one result,then click "query results" button,but return to query page | Li, Yue | 2008-08-28 10:54 | 2 | bar: 2008-08-29 to 2008-09-03
6323 | [WX] Cannot display self-defined index correctly. | Liu, Travis | 2008-08-28 16:53 | 2 | bar: 2008-08-29 to 2008-09-03
6490 | [54 Legacy][AppGen] AppGen need to restart to get the latest change. | Liu, Travis | 2008-08-28 17:57 | 3 | bar: 2008-08-29 to 2008-09-03
6965 | XSAdmin wizard will cause error | Teng, Kevin | 2008-08-28 13:38 | 2 | bar: 2008-08-29 to 2008-09-04
6968 | The direction is wrong in path dialog box | Teng, Kevin | 2008-08-28 18:09 | 2 | bar: 2008-08-29 to 2008-09-04
6456 | [Application Generator]cannot add license group while adding new user | Li, Yue | 2008-08-30 13:17 | 2 | bar: 2008-08-29 to 2008-09-03
6429 | [54 Legacy][AX]Email mulitiple tiffs as XPS will only have 1 page | Teng, Kevin | 2008-08-29 15:24 | 2 | bar: 2008-08-29 to 2008-09-04
6438 | [54 Legacy][Document Manager]Stay Logged into AX for long period of time,license info shows no user license in use | Li, Yue | 2008-09-03 06:31 | 2 | bar: 2008-09-03 to 2008-09-05
6986 | First time submit Full Text Search, will ignore the OCR language | Teng, Kevin | 2008-09-01 10:56 | 2 | bar: 2008-09-03 to 2008-09-04
6439 | [54 Legacy][Document Manager]set license group for DataSource is not available | Li, Yue | 2008-09-04 03:34 | 2 | bar: 2008-09-04 to 2008-09-09
6566 | [54 legacy][license server]could not back to custom setup page during installation of new build | Li, Yue | 2008-09-05 12:32 | 2 | bar: 2008-09-08 to 2008-09-09
6985 | Full text search can't locate the keywords | Teng, Kevin | 2008-09-05 18:06 | 2 | bar: 2008-09-08
7030 | Query CAQ will make AX crash | Teng, Kevin | 2008-09-05 16:32 | 1 | bar: 2008-09-08 to 2008-09-09
6341 | [WX] check componet get an error | Li, Yue | 2008-09-09 09:33 | 2 | bar: 2008-09-09 to 2008-09-11; 2008-09-16
6911 | If cannot find bin file, IRC viewer displays unreadable code. | Liu, Travis | 2008-09-08 16:19 | 2 | bar: 2008-09-09 to 2008-09-11
7077 | It need to Click Details button twice to make it work in Verify dialogue box | Teng, Kevin | 2008-09-09 13:39 | 2 | bar: 2008-09-10 to 2008-09-11
6824 | Error will occur when install AX | Teng, Kevin | 2008-09-09 14:12 | 1 | bar: 2008-09-10 to 2008-09-11
6312 | [Document manager]Export tab UI in Configuration is not displayed correctly | Li, Yue | 2008-09-15 15:27 | 2 | bar: 2008-09-16 to 2008-09-17
6318 | [Document Manager]print tab UI in configuration display is incorrectly | Li, Yue | 2008-09-15 15:25 | 3 | bar: 2008-09-16 to 2008-09-17
6482 | [AppGen]new application page UI is not correct | Li, Yue | 2008-09-15 16:21 | 2 | bar: 2008-09-16 to 2008-09-17
6483 | [AppGen]new application path UI is not correct | Li, Yue | 2008-09-15 16:22 | 2 | bar: 2008-09-16 to 2008-09-17
6346 | [WX] There are many 'missing strings' in administration page. | Liu, Travis | 2008-09-15 15:32 | 2 | bar: 2008-09-16 to 2008-09-17; 2008-09-19 to 2008-09-22
6347 | [WX] Exception page pop up after clicking remove retention hold button in administration page. | Liu, Travis | 2008-09-15 15:37 | 1 | bar: 2008-09-16 to 2008-09-17; 2008-09-19 to 2008-09-22
6348 | [WX] The hint info of remove retention hold button is not localized. | Liu, Travis | 2008-09-15 15:45 | 3 | bar: 2008-09-16 to 2008-09-17; 2008-09-19 to 2008-09-22
6349 | [WX] Part of the menus in the administration page are not localized into Chinese. | Liu, Travis | 2008-09-15 15:54 | 3 | bar: 2008-09-16 to 2008-09-17; 2008-09-19 to 2008-09-22
6357 | [AX] Missing part of toolbar menu. | Liu, Travis | 2008-09-13 19:50 | 1 | bar: 2008-09-16 to 2008-09-18
6414 | [Admin]Administrator is not translated | Teng, Kevin | 2008-09-15 16:19 | 2 | bar: 2008-09-16 to 2008-09-18
6417 | [AX]New Cross App Query menu should not under New Document | Teng, Kevin | 2008-09-15 16:20 | 2 | bar: 2008-09-16 to 2008-09-18
6378 | [Admin] AX Admin cannot launch successfully in Vista. | Liu, Travis | 2008-09-16 17:12 | 2 | bar: 2008-09-17; 2008-09-19 to 2008-09-22
6276 | [AX] Open help failed. | Liu, Travis | 2008-09-18 01:18 | 2 | bar: 2008-09-19 to 2008-09-22
6296 | [AX] Launch help failed in document properties window. | Liu, Travis | 2008-09-18 01:17 | 2 | bar: 2008-09-19 to 2008-09-22
7190 | [Storage and Retention installer]UI is 5.40 SP1 and no license message | Li, Yue | 2008-09-18 10:02 | 2 | bar: 2008-09-19 to 2008-09-22
7177 | There is an error page when try to open administration page. | Liu, Travis | 2008-09-18 09:54 | 1 | bar: 2008-09-19 to 2008-09-22
6914 | [54 Legacy]Help in revision history can't be launched | Teng, Kevin | 2008-09-19 01:26 | 2 | bar: 2008-09-19 to 2008-09-24
7103 | The FullText result dialog box behavior for Verity K2 is not same as ProIndex | Teng, Kevin | 2008-09-18 10:22 | 2 | bar: 2008-09-19 to 2008-09-24
7179 | Admin will crash if don't select licsense server when adding a new datasource | Teng, Kevin | 2008-09-18 15:02 | 3 | bar: 2008-09-19 to 2008-09-24
7102 | The total hit number is not correct | Teng, Kevin | 2008-09-19 11:09 | 2 | bar: 2008-09-22 to 2008-09-24
7212 | The icon in Create table dialogbox should be a question mark | Teng, Kevin | 2008-09-22 11:43 | 3 | bar: 2008-09-23 to 2008-09-25
7244 | [AppGen]can not add new application | Li, Yue | 2008-09-24 14:25 | 1
7180 | Configuration Validation dialog is not big enough | Teng, Kevin | 2008-09-24 15:28 | 3 | bar: 2008-10-06
7263 | Input full app name will cause error | Teng, Kevin | 2008-09-26 14:01 | 3 | bar: 2008-10-06
7268 | Full Text search using special keyword cannot hilight the results | Teng, Kevin | 2008-09-26 10:58 | 2 | bar: 2008-10-06
7244 | [AppGen]can not add new application | Li, Yue | 2008-09-24 14:25 | 1 | bar: 2008-10-13 to 2008-10-14
7280 | [WX] select one record right click, print, but the endorsement is not printed | Li, Yue | 2008-10-10 05:39 | 2 | bar: 2008-10-13 to 2008-10-15
7370 | [legacy] Drive maps will mess up after cancel browsing. | Liu, Travis | 2008-10-08 16:23 | 2 | bar: 2008-10-13 to 2008-10-15
7371 | [Legacy] The changing confirm window should contains a Cancel button. | Liu, Travis | 2008-10-08 14:22 | 3 | bar: 2008-10-13 to 2008-10-15
7372 | [Legacy] The folder browser dialog should appear as a modal dialog. | Liu, Travis | 2008-10-08 16:22 | 3 | bar: 2008-10-13 to 2008-10-15
7364 | Configuration Validation dialog should be translated | Teng, Kevin | 2008-10-06 15:12 | 2 | bar: 2008-10-13 to 2008-10-14
6429 | [54 Legacy][AX]Email mulitiple tiffs as XPS will only have 1 page | Teng, Kevin | 2008-10-10 05:56 | 2 | bar: 2008-10-13 to 2008-10-14
7184 | using special keyword, it will cause com error | Teng, Kevin | 2008-10-09 02:18 | 2 | bar: 2008-10-13 to 2008-10-14
7262 | License server doesn't work if installed on updated Win2k3EN | Teng, Kevin | 2008-10-10 06:57 | 1 | bar: 2008-10-13 to 2008-10-14
7268 | [AX]Full Text search using special keyword cannot hilight the results | Teng, Kevin | 2008-09-26 10:58 | 2 | bar: 2008-10-13 to 2008-10-14
6668 | Can't render the document which saved into AX through ODMA | Teng, Kevin | 2008-09-27 15:36 | 2 | bar: 2008-10-13 to 2008-10-14
7366 | WXJ2 can't login | Teng, Kevin | 2008-10-08 13:38 | 1 | bar: 2008-10-13 to 2008-10-14
6298 | [AXadmin]verify license server,on License server Information window Detailes button covers part of Close button | Li, Yue | 2008-10-13 13:15 | 2 | bar: 2008-10-14 to 2008-10-15
6369 | [document Manager]OCR tab in configuration is not with pseudo string | Li, Yue | 2008-10-13 13:20 | 2 | bar: 2008-10-14 to 2008-10-15
6475 | [AppGen]create new Data types page display is not correct | Li, Yue | 2008-10-13 13:22 | 2 | bar: 2008-10-14 to 2008-10-15
6482 | [AppGen]new application page UI is not correct | Li, Yue | 2008-10-13 13:25 | 2 | bar: 2008-10-14 to 2008-10-15
6477 | [AppGen] Export feature cannot work correctly for Chinese. | Liu, Travis | 2008-10-13 13:24 | 1 | bar: 2008-10-14 to 2008-10-15
7391 | [WXJ2] Useless debug information pop up when switch between different data source. | Liu, Travis | 2008-10-13 14:15 | 2 | bar: 2008-10-14 to 2008-10-15
6425 | [AX] There is a meaningless line in the Export sub menu. | Liu, Travis | 2008-10-13 13:21 | 2 | bar: 2008-10-14 to 2008-10-15
6428 | [AX] Menu group is not correct in Scan menu. | Liu, Travis | 2008-10-13 13:22 | 2 | bar: 2008-10-14 to 2008-10-15
6345 | [WX] Status bar is not localized. | Liu, Travis | 2008-10-13 13:16 | 3 | bar: 2008-10-14 to 2008-10-16; 2008-10-20 to 2008-10-21
6350 | [WX] Part of the monitor parameters of WX.Net are not localized into Chinese. | Liu, Travis | 2008-10-13 13:16 | 2 | bar: 2008-10-14 to 2008-10-16; 2008-10-20 to 2008-10-21
6527 | [WX] There is no hint info for retention hold toolbar button. | Liu, Travis | 2008-10-13 13:29 | 2 | bar: 2008-10-14 to 2008-10-15
6528 | [WX] The retention hold feature cannot works correctly in Simplified Chinese Evn. | Liu, Travis | 2008-10-13 13:30 | 1 | bar: 2008-10-14 to 2008-10-15
6531 | [WX] The hint info of "Set retetion" toolbar button is not localized into Chinese. | Liu, Travis | 2008-10-13 13:31 | 2 | bar: 2008-10-14 to 2008-10-15
6532 | [WX] Exception page pop up after clicking "Put Selected Documents on Retention" toolbar button in result set page. | Liu, Travis | 2008-10-13 13:32 | 1 | bar: 2008-10-14 to 2008-10-15
6617 | [Translation][AX] IRC viewer context menu is not localized into Chinese. | Liu, Travis | 2008-10-13 13:55 | 2 | bar: 2008-10-14 to 2008-10-15
6631 | [Translation][AX] Application properties window is not localized into Simplified Chinese. | Liu, Travis |  | 2 | bar: 2008-10-14 to 2008-10-21
7426 | Render error when click "Printer friendly view" menu for a picture type document. | Liu, Travis | 2008-10-14 17:23 | 2 | bar: 2008-10-15 to 2008-10-21
7427 | Stack overflow error message pop up when click "Printer friendly view" menu for a COLD type document. | Liu, Travis | 2008-10-14 17:23 | 2 | bar: 2008-10-15 to 2008-10-21
7428 | A blank window will a "null" pops up when click "Merge PDF for print" menu. | Liu, Travis | 2008-10-14 16:41 | 2 | bar: 2008-10-15 to 2008-10-21
7388 | [XsAdmin]Go back will not have DB String Type choice when adding a new datasource | Teng, Kevin | 2008-10-14 15:24 | 3 | bar: 2008-10-15 to 2008-10-21
7178 | The font in UserPID table is not correct(106) | Teng, Kevin | 2008-10-15 05:46 | 3 | bar: 2008-10-15 to 2008-10-21
7183 | Full Text search can't highlight the keyword for pdfs | Teng, Kevin | 2008-10-15 03:25 | 2 | bar: 2008-10-15 to 2008-10-16
7262 | License server doesn't work if installed on updated Win2k3EN | Teng, Kevin | 2008-10-10 06:57 | 1 | bar: 2008-10-15 to 2008-10-16
7268 | [AX]Full Text search using special keyword cannot hilight the results | Teng, Kevin | 2008-09-26 10:58 | 2 | bar: 2008-10-15 to 2008-10-16
7383 | [WXJ2]Click User Settings will have exception in Tomcat console | Teng, Kevin | 2008-10-10 15:44 | 2 | bar: 2008-10-15 to 2008-10-21
7366 | WXJ2 can't login | Teng, Kevin | 2008-10-08 13:38 | 1 | bar: 2008-10-15 to 2008-10-16
7378 | [WXJ2]Delete selected documents won't work well | Teng, Kevin | 2008-10-10 16:53 | 2 | bar: 2008-10-15 to 2008-10-21
7385 | [WXJ2]The version on starting logo should not be 5.4 | Teng, Kevin | 2008-10-13 13:29 | 2 | bar: 2008-10-15 to 2008-10-21
7419 | [WXJ2]Can't import a special COLD file using IRC mode | Teng, Kevin | 2008-10-14 16:15 | 2 | bar: 2008-10-15 to 2008-10-21
6356 | [AppGen]Click Index Image File Setup and then click another app will say Application has changed. | Teng, Kevin | 2008-10-13 13:17 | 2 | bar: 2008-10-15 to 2008-10-16
6364 | [WX]Query page index hints are not translated | Teng, Kevin | 2008-10-13 13:19 | 2 | bar: 2008-10-15 to 2008-10-16
6365 | [WX]Index hints on index page are not translated | Teng, Kevin | 2008-10-13 13:19 | 2 | bar: 2008-10-15 to 2008-10-16
6427 | [AX]View menu is not same as CM54 | Teng, Kevin | 2008-10-13 13:21 | 2 | bar: 2008-10-15 to 2008-10-16
6429 | [54 Legacy][AX]Email mulitiple tiffs as XPS will only have 1 page | Teng, Kevin | 2008-10-10 05:56 | 2 | bar: 2008-10-15 to 2008-10-16
6495 | [54 Legacy][AX] AX will crash if import a specified file | Teng, Kevin | 2008-10-14 03:57 | 3 | bar: 2008-10-15 to 2008-10-21
6482 | [AppGen]new application page UI is not correct | Li, Yue | 2008-10-16 02:19 | 2 | bar: 2008-10-16 to 2008-10-20
7444 | [WX]update from 5.5 to 6.0 failed | Li, Yue | 2008-10-15 10:39 | 2 | bar: 2008-10-16 to 2008-10-17
7445 | [WX]installation picture information is 5.5 | Li, Yue | 2008-10-15 10:40 | 2 | bar: 2008-10-16 to 2008-10-17
7423 | [AX]export UI on win2k8 is different with winXP or win2k3 | Li, Yue | 2008-10-15 15:21 | 2 | bar: 2008-10-16 to 2008-10-20
7443 | [document manager]print dialog is displayed, but there is no page range and hide annotation check box | Li, Yue | 2008-10-15 15:14 | 2 | bar: 2008-10-16 to 2008-10-17
7277 | [WX]print Endorsement Text can not be set 80 characters per line and 10 lines | Li, Yue | 2008-10-16 06:03 | 2 | bar: 2008-10-16 to 2008-10-21
7415 | Error message pop up when adding/deleting pages. | Liu, Travis | 2008-10-15 09:55 | 2 | bar: 2008-10-16 to 2008-10-21
7447 | Switch to application path tab will cause AppGen crash. | Liu, Travis | 2008-10-15 15:13 | 1 | bar: 2008-10-16 to 2008-10-21
7418 | Error message pop up when try to delete a document revision. | Liu, Travis | 2008-10-15 09:56 | 2 | bar: 2008-10-16 to 2008-10-21
7440 | [XsAdmin]Change the session Time-Out, the save button is still disabled | Teng, Kevin | 2008-10-15 16:57 | 3 | bar: 2008-10-16 to 2008-10-21
6915 | The font is ugly , and missing some words in check in window(105) | Teng, Kevin | 2008-10-16 02:13 | 3 | bar: 2008-10-16 to 2008-10-21
7178 | The font in UserPID table is not correct(106) | Teng, Kevin | 2008-10-15 05:46 | 3 | bar: 2008-10-16 to 2008-10-21
7183 | Full Text search can't highlight the keyword for pdfs | Teng, Kevin | 2008-10-15 03:25 | 2 | bar: 2008-10-16 to 2008-10-21
7376 | [WXJ2]Can't delete document | Teng, Kevin | 2008-10-15 09:53 | 2 | bar: 2008-10-16 to 2008-10-21
7377 | [WXJ2]"unknown user name or bad password" will display if query on DEMO db | Teng, Kevin | 2008-10-15 11:19 | 1 | bar: 2008-10-16 to 2008-10-21
7389 | [WXJ2]Query on Demo db will cause error (Win2008) | Teng, Kevin | 2008-10-15 10:13 | 2 | bar: 2008-10-16 to 2008-10-21
7467 | Add special COLD will be recognized as foreign file. | Liu, Travis | 2008-10-17 16:39 | 2 | bar: 2008-10-20 to 2008-10-21
7500 | [Translation]Reorder need to be translated | Teng, Kevin | 2008-10-17 10:34 | 2 | bar: 2008-10-20 to 2008-10-21
7416 | [WXJ2]Can't go back to Index view | Teng, Kevin | 2008-10-17 17:14 | 2 | bar: 2008-10-20 to 2008-10-21
6474 | [54 Legacy][Document Manager]email document,set text as image and screen/printer as Image,open the sent document it displays nothing | Li, Yue |  | 2 | bar: 2008-10-23 to 2008-10-24
7517 | [AX]install AX 6.0.34 fail on W2k8 Chinese platform | Li, Yue | 2008-10-22 10:08 | 2 | bar: 2008-10-23 to 2008-10-24
7477 | [document manager]batch index(list) causes Document Manager crash when there is more than one file | Li, Yue | 2008-10-21 13:50 | 2 | bar: 2008-10-23 to 2008-10-24
7526 | [AX]index server is crash when click OCR tab | Li, Yue | 2008-10-22 13:37 | 1 | bar: 2008-10-23 to 2008-10-24
7462 | [document manager]email annotated TIF as XPS with hide annotations, XPS file still has annotation | Li, Yue | 2008-10-20 11:02 | 2 | bar: 2008-10-23 to 2008-10-24
7540 | [WXJ2] Tooltip on login page shows the wrong version info. | Liu, Travis | 2008-10-22 10:09 | 2 | bar: 2008-10-23 to 2008-10-24
7530 | [Translation] Error message is not localized into Chinese. | Liu, Travis | 2008-10-22 14:14 | 3 | bar: 2008-10-23 to 2008-10-24
7539 | Tooltip on login page shows the wrong version info. | Liu, Travis | 2008-10-22 00:05 | 2 | bar: 2008-10-23 to 2008-10-24
6316 | [AX] Spell checker cannot work correctly for Chinese. | Liu, Travis |  | 2 | bar: 2008-10-23 to 2008-10-24
6368 | [WX&AX] Unreadable code occurs in text form overlay. | Liu, Travis |  | 2 | bar: 2008-10-23 to 2008-10-29
6474 | [54 Legacy][Document Manager]email document,set text as image and screen/printer as Image,open the sent document it displays nothing | Li, Yue |  | 2 | bar: 2008-10-24 to 2008-10-29
7638 | [AXAdmin]add data source the password is appear with plain text | Li, Yue | 2008-10-24 05:05 | 2 | bar: 2008-10-24 to 2008-10-29
7277 | [WX]print Endorsement Text can not be set 80 characters per line and 10 lines | Li, Yue | 2008-10-23 23:08 | 2 | bar: 2008-10-24 to 2008-10-29
7618 | [CHN] [Translation] The error message of spell checker is not localized into Chinese. | Liu, Travis | 2008-10-23 11:44 | 3 | bar: 2008-10-24 to 2008-10-29
7467 | Add special COLD will be recognized as foreign file. | Liu, Travis | 2008-10-24 05:27 | 2 | bar: 2008-10-24 to 2008-10-29
7417 | [WXJ2]Double click app, it will turn to the end of this page | Teng, Kevin | 2008-10-22 16:47 | 3 | bar: 2008-10-24 to 2008-10-29
7420 | [WXJ2]Can't render COLD file in Thin client | Teng, Kevin | 2008-10-22 16:47 | 3 | bar: 2008-10-24 to 2008-10-29
7439 | [WXJ2]In result page, the number and pagination are not in the same line | Teng, Kevin | 2008-10-22 17:10 | 3 | bar: 2008-10-24 to 2008-10-29
7501 | [MigWiz]Error occurs when performing Migration | Teng, Kevin | 2008-10-20 11:50 | 1 | bar: 2008-10-24 to 2008-10-29
7525 | [Admin]There is no title on last page of Add new datasource | Teng, Kevin | 2008-10-21 16:11 | 3 | bar: 2008-10-24 to 2008-10-29
6429 | [54 Legacy][AX]Email mulitiple tiffs as XPS will only have 1 | Teng, Kevin | 2008-10-23 21:39 | 2 | bar: 2008-10-24 to 2008-10-29
6268 | [AX]Text Search doesn't work well | Teng, Kevin |  | 1 | bar: 2008-10-24 to 2008-10-29
6317 | [AX]Add Text rubber stamp will not add the whole stamp | Teng, Kevin |  | 3 | bar: 2008-10-24 to 2008-10-29
6618 | [AX]Fuzzing search for Chinese character doesn't work | Teng, Kevin |  | 2 | bar: 2008-10-24 to 2008-10-29
6985 | Full text search can't locate the keywords | Teng, Kevin | 2008-10-24 05:23 | 2 | bar: 2008-10-24 to 2008-10-29
7183 | Full Text search can't highlight the keyword for pdfs | Teng, Kevin | 2008-10-15 03:25 | 2 | bar: 2008-10-24 to 2008-10-29
7268 | [AX]Full Text search using special keyword cannot hilight the results | Teng, Kevin | 2008-10-24 05:24 | 2 | bar: 2008-10-24 to 2008-10-29
7474 | [AX]AX will crash if input Chinese charactor and submit in FT | Teng, Kevin | 2008-10-21 04:34 | 1 | bar: 2008-10-24 to 2008-10-29
7502 | [Installation]If change install path, it will cause CMLsClient.dll error | Teng, Kevin | 2008-10-21 13:41 | 2 | bar: 2008-10-24 to 2008-10-29
7521 | Can't not add Demo datasource if change AX install path | Teng, Kevin | 2008-10-23 21:05 | 1 | bar: 2008-10-24 to 2008-10-29
7538 | [ArchiveWizard]Can't open doc if don't Archive without Premaster Directory | Teng, Kevin | 2008-10-23 17:28 | 2 | bar: 2008-10-24 to 2008-10-29
7541 | [AX]Text Search can't find English keywords | Teng, Kevin | 2008-10-22 15:16 | 2 | bar: 2008-10-24 to 2008-10-29
7422 | [WX]Import using Thin Client mode and IRC mode will have different behaviors | Teng, Kevin | 2008-10-24 05:27 | 2 | bar: 2008-10-24 to 2008-10-29
7656 | [WXJ2]Can't install Webservice | Teng, Kevin | 2008-10-28 | 1 | bar: 2008-10-28 to 2008-10-29
7617 | [CHN] Cannot add text annotation in Image Capture. | Liu, Travis | 2008-10-28 | 1 | bar: 2008-10-28 to 2008-10-29
7520 | Can not install AX Storage and Retention under win2008. | Liu, Travis | bar: 2008-10-29 to 2008-10-30
7636 | [CHN] Chinese index value cannot be exported correctly by using "Export selected document indexes". | Liu, Travis | bar: 2008-10-29 to 2008-10-30
7637 | Thumbnail does not refresh after adding/deleting pages. | Liu, Travis | bar: 2008-10-29 to 2008-10-30
7413 | [WXJ2]Thumbnail is not correct when creating new document form batch. | Liu, Travis | bar: 2008-10-29 to 2008-10-30
7386 | [LicenseServer]LicenseServer service can't be started in Win2k8 | Teng, Kevin | 2008-10-25 03:08 | bar: 2008-10-29 to 2008-10-30
7529 | [IndexServer]Win2k8 miss some credentials | Teng, Kevin | bar: 2008-10-29 to 2008-10-30
7656 | [WXJ2]Can't install Webservice | Teng, Kevin | 2008-10-28 01:07 | bar: 2008-10-29 to 2008-10-30
7544 | [AX]Wild Card Search for Text Search doesn't work for Chinese | Teng, Kevin | bar: 2008-10-29 to 2008-10-30
6474 | [54 Legacy][Document Manager]email document,set text as image and screen/printer as Image,open the sent document it displays nothing | Li, Yue | 2008-10-25 04:34 | 2 | bar: 2008-10-29 to 2008-10-30
7542 | [CHN][Document Manager]Chinese wild query value will be disorder if logoff then login application | Li, Yue | 2008-10-28 11:42 | 2 | bar: 2008-10-29 to 2008-10-30
7638 | [AXAdmin]add data source the password is appear with plain text | Li, Yue | 2008-10-24 05:05 | 2 | bar: 2008-10-29 to 2008-10-30
7277 | [WX]print Endorsement Text can not be set 80 characters per line and 10 lines | Li, Yue | 2008-10-23 23:08 | 2 | bar: 2008-10-29 to 2008-10-30
7618 | [CHN] [Translation] The error message of spell checker is not localized into Chinese. | Liu, Travis | 2008-10-23 11:44 | 3 | bar: 2008-10-29 to 2008-10-30
7617 | [CHN] Cannot add text annotation in Image Capture. | Liu, Travis | 2008-10-25 03:00 | 1 | bar: 2008-10-29 to 2008-10-30
7467 | Add special COLD will be recognized as foreign file. | Liu, Travis | 2008-10-24 05:27 | 2 | bar: 2008-10-29 to 2008-10-30
7420 | [WXJ2]Can't render COLD file in Thin client | Teng, Kevin | 2008-10-22 16:47 | 3 | bar: 2008-10-29 to 2008-11-03
7439 | [WXJ2]In result page, the number and pagination are not in the same line | Teng, Kevin | 2008-10-22 17:10 | 3 | bar: 2008-10-29 to 2008-11-03
7656 | [WXJ2]Can't install Webservice | Teng, Kevin | 2008-10-28 01:07 | 1 | bar: 2008-10-29 to 2008-11-03
6985 | Full text search can't locate the keywords | Teng, Kevin | 2008-10-24 05:23 | 2 | bar: 2008-10-29 to 2008-10-31
7183 | Full Text search can't highlight the keyword for pdfs | Teng, Kevin | 2008-10-15 03:25 | 2 | bar: 2008-10-29 to 2008-10-31
7268 | [AX]Full Text search using special keyword cannot hilight the results | Teng, Kevin | 2008-10-24 05:24 | 2 | bar: 2008-10-29 to 2008-10-31
7474 | [AX]AX will crash if input Chinese charactor and submit in FT | Teng, Kevin | 2008-10-21 04:34 | 1 | bar: 2008-10-29 to 2008-10-31
7521 | Can't not add Demo datasource if change AX install path | Teng, Kevin | 2008-10-23 21:05 | 1 | bar: 2008-10-29 to 2008-11-03
7422 | [WX]Import using Thin Client mode and IRC mode will have different behaviors | Teng, Kevin | 2008-10-24 05:27 | 2 | bar: 2008-10-29 to 2008-10-31
6268 | [AX]Text Search doesn't work well | Teng, Kevin |  | 1 | bar: 2008-10-29 to 2008-10-31
7503 | [Installation]Remove Render Server will cause error | Teng, Kevin | 2008-10-29 13:11 | 2 | bar: 2008-10-30 to 2008-10-31
7523 | [Admin]Can't login XsAdmin if change AX install path | Teng, Kevin | 2008-10-29 13:22 | 1 | bar: 2008-10-30 to 2008-10-31
7180 | Configuration Validation dialog is not big enough | Teng, Kevin | 2008-10-29 13:23 | 3 | bar: 2008-10-30 to 2008-10-31
7658 | [AX] New a Chinese Rubber stamp will display bad code | Teng, Kevin | 2008-10-29 16:48 | 2 | bar: 2008-10-30 to 2008-11-03
7696 | Cannot render document correctly. | Liu, Travis | 2008-10-30 07:39 | 1 | bar: 2008-10-30 to 2008-11-03
7695 | [CHN][AXadmin]GUI:open admin splash sreen is AX5.5 and help window is AX5.5 | Li, Yue | 2008-10-30 11:21 | 2 | bar: 2008-10-31 to 2008-11-03
7413 | [WXJ2]Thumbnail is not correct when creating new document form batch. | Liu, Travis | 2008-10-30 16:43 | 2 | bar: 2008-10-31 to 2008-11-03
7717 | [CHN] Cannot add Chinese Text rubber stamp. | Liu, Travis | 2008-10-30 14:03 | 1 | bar: 2008-10-31 to 2008-11-03
7700 | Tab order of 3 Verity textboxes is not correct | Teng, Kevin | 2008-10-30 14:02 | 3 | bar: 2008-10-31 to 2008-11-03
7701 | [AppGen]Can't change the Verity K2 server name | Teng, Kevin | 2008-10-30 13:24 | 1 | bar: 2008-10-31 to 2008-11-03
7718 | [AutoIndex]Auto Index/Key Reference Import could not identify Unicode text file | Li, Yue | 2008-11-01 03:02 | 2 | bar: 2008-11-03 to 2008-11-04
7655 | [WX]could not add Text Annotations in IRC | Li, Yue | 2008-11-01 04:36 | 2 | bar: 2008-11-03 to 2008-11-04
7657 | [WX]unsaved annotation is lost after click Select | Li, Yue | 2008-11-01 04:31 | 2 | bar: 2008-11-03 to 2008-11-04
7696 | Cannot render document correctly. | Liu, Travis | 2008-10-30 07:39 | 1 | bar: 2008-11-03 to 2008-11-04
7413 | [WXJ2]Thumbnail is not correct when creating new document form batch. | Liu, Travis | 2008-10-30 16:43 | 2 | bar: 2008-11-03 to 2008-11-04
6985 | Full text search can't locate the keywords | Teng, Kevin | 2008-11-01 02:07 | 2 | bar: 2008-11-03 to 2008-11-04
7544 | [AX]Wild Card Search for Text Search doesn't work for Chinese | Teng, Kevin | 2008-11-01 02:11 | 2 | bar: 2008-11-03 to 2008-11-04
7738 | [WXJ2]Can't load thumbnail control browse in Chinese OS | Teng, Kevin | 2008-10-31 17:47 | 3 | bar: 2008-11-03 to 2008-11-06
7736 | [installation]there is no Third Paty Components foloder in 6.0.043 | Li, Yue | 2008-11-04 09:41 | 2 | bar: 2008-11-04 to 2008-11-06
7739 | [CHN][AX]there is no translation in Document Manager/Image Capture license information | Li, Yue | 2008-11-03 16:03 | 2 | bar: 2008-11-04 to 2008-11-07
7690 | [CHN][WX]could not add Text Annotations in IRC | Li, Yue | 2008-11-03 14:13 | 2 | bar: 2008-11-04 to 2008-11-06
7740 | [CHN] AX Rendering Server Configuration UI use wrong text alignment. | Liu, Travis | 2008-11-03 15:57 | 2 | bar: 2008-11-04 to 2008-11-06
7753 | [WXJ2] Ircviewer doesn't refresh after delete a page from batch | Liu, Travis | 2008-11-03 13:49 | 2 | bar: 2008-11-04 to 2008-11-07
7616 | [AX]Modify the index value, the Save button will still be disabled | Teng, Kevin | 2008-11-03 16:02 | 3 | bar: 2008-11-04 to 2008-11-05
7722 | Can't start Document Manager if user is not an Administrator | Teng, Kevin | 2008-11-03 10:55 | 1 | bar: 2008-11-04 to 2008-11-05
7698 | DemoDB should be updated to 6.0 | Teng, Kevin | 2008-11-03 14:31 | 2 | bar: 2008-11-04 to 2008-11-05
7718 | [AutoIndex]Auto Index/Key Reference Import could not identify Unicode text file | Li, Yue | 2008-11-01 03:02 | 2 | bar: 2008-11-05 to 2008-11-06
7695 | [CHN][AXadmin]GUI:open admin splash sreen is AX5.5 and help window is AX5.5 | Li, Yue | 2008-11-04 17:35 | 2 | bar: 2008-11-05 to 2008-11-06
7413 | [WXJ2]Thumbnail is not correct when creating new document form batch. | Liu, Travis | 2008-11-04 17:14 | 2 | bar: 2008-11-05 to 2008-11-07
7689 | [WX&AX] The forms that was saved in the demoDB is in ansi text format, and they will be converted to some unreadable code in Chinese (non-Western Language) OS. | Liu, Travis | 2008-11-05 05:55 | 2 | bar: 2008-11-05 to 2008-11-06
7702 | [CHN] Some tool bar icons cannot be fully displayed in Vista. | Liu, Travis | 2008-11-04 17:44 | 2 | bar: 2008-11-05 to 2008-11-06
7703 | Version number is not correct for AX and Image Capture. | Liu, Travis | 2008-11-04 14:04 | 3 | bar: 2008-11-05 to 2008-11-06
7725 | [AX]Full Text Search using one Chinese character will cause COM error | Teng, Kevin | 2008-11-04 11:07 | 1 | bar: 2008-11-05 to 2008-11-06
7756 | [FullText]Can't perform correct Exact phrase search | Teng, Kevin | 2008-11-04 17:03 | 2 | bar: 2008-11-05 to 2008-11-07
7757 | [FullText]It will cause COM error if add blank between 2 Chinese words | Teng, Kevin | 2008-11-04 17:03 | 2 | bar: 2008-11-05 to 2008-11-06
7758 | [FullText]Can't perform Expression Search | Teng, Kevin | 2008-11-04 17:03 | 2 | bar: 2008-11-05 to 2008-11-07
7759 | [FullText]Can't perform correct All Words Search | Teng, Kevin | 2008-11-04 17:03 | 2 | bar: 2008-11-05 to 2008-11-07
7760 | [FullText]Can't Search some characters | Teng, Kevin | 2008-11-04 17:14 | 2 | bar: 2008-11-05 to 2008-11-06
7761 | [FullText]Textbox is not easy to re-edit | Teng, Kevin | 2008-11-04 17:18 | 3 | bar: 2008-11-05 to 2008-11-06
7614 | [CHN]Chinese COLD document can't be rendered correctly | Teng, Kevin | 2008-11-05 05:51 | 2 | bar: 2008-11-05 to 2008-11-06
7615 | [AX]Save query can't perform correct query | Teng, Kevin | 2008-11-04 10:32 | 2 | bar: 2008-11-05 to 2008-11-06
6268 | [AX]Text Search for PDF file doesn't work well | Teng, Kevin | 2008-11-04 23:32 | 1 | bar: 2008-11-05 to 2008-11-07
7183 | Full Text search can't highlight the keyword for pdfs | Teng, Kevin | 2008-11-05 02:32 | 2 | bar: 2008-11-05 to 2008-11-07
7699 | Can't start XsAdmin if user is not an Administrator | Teng, Kevin | 2008-11-05 03:44 | 1 | bar: 2008-11-05 to 2008-11-06
7695 | [CHN][AXadmin]GUI:open admin splash sreen is AX5.5 and help window is AX5.5 | Li, Yue | 2008-11-05 21:28 | 2 | bar: 2008-11-06 to 2008-11-12
7771 | [CHN][WX]demo license is displayed, but it is not correct | Li, Yue | 2008-11-05 14:45 | 2 | bar: 2008-11-06 to 2008-11-12
7772 | [CHN] Error message pop up when opening WX monitor. | Liu, Travis | 2008-11-05 15:38 | 2 | bar: 2008-11-06 to 2008-11-12
7689 | [WX&AX] The forms that was saved in the demoDB is in ansi text format, and they will be converted to some unreadable code in Chinese (non-Western Language) OS. | Liu, Travis | 2008-11-06 00:46 | 2 | bar: 2008-11-06 to 2008-11-12
7741 | [CHN] Rubber stamp does not support Chinese punctuation (full width). | Liu, Travis | 2008-11-06 00:10 | 3 | bar: 2008-11-06 to 2008-11-12
7743 | [Installation]If change AX install path, some folders will still remain on C:\ | Teng, Kevin | 2008-11-05 15:35 | 2 | bar: 2008-11-06 to 2008-11-07
7774 | [WX]Can't use Search range | Teng, Kevin | 2008-11-05 16:43 | 2 | bar: 2008-11-06 to 2008-11-12
7775 | [WX]Can't use Search List | Teng, Kevin | 2008-11-05 16:43 | 2 | bar: 2008-11-06 to 2008-11-12
7776 | [CHN]In Email dialog box, the translation of "To" is not correct | Teng, Kevin | 2008-11-05 17:04 | 2 | bar: 2008-11-06 to 2008-11-12
7738 | [WXJ2]Can't load thumbnail control browse in Chinese OS | Teng, Kevin | 2008-10-31 17:47 | 3 | bar: 2008-11-06 to 2008-11-07
7658 | [AX] New a Chinese Rubber stamp will display bad code | Teng, Kevin | 2008-11-06 00:10 | 2 | bar: 2008-11-06 to 2008-11-12
7754 | [XsAdmin] Can't open XsAdmin in Vista | Teng, Kevin | 2008-11-06 04:54 | 1 | bar: 2008-11-06 to 2008-11-07
7807 | [WX]open RTF file, right area render page description is not correct | Li, Yue | 2008-11-06 22:27 | 2 | bar: 2008-11-07 to 2008-11-10
7803 | AxRegis.exe will throw error on Vista. | Liu, Travis | 2008-11-07 04:07 | 2 | bar: 2008-11-07 to 2008-11-10
7783 | [ImageCapture]About window is too ugly | Shi, Simon |  | 3 | bar: 2008-11-07 to 2008-11-10
7614 | [CHN]Chinese COLD document can't be rendered correctly | Teng, Kevin | 2008-11-07 04:41 | 2 | bar: 2008-11-07 to 2008-11-11
7770 | [WX]Printing log contains some useless information | Teng, Kevin | 2008-11-06 15:53 | 3 | bar: 2008-11-07 to 2008-11-12
7758 | [FullText]Can't perform Expression Search | Teng, Kevin | 2008-11-04 17:03 | 2 | bar: 2008-11-07 to 2008-11-13
7784 | [UserProfile]About window is too ugly | Teng, Kevin |  | 3 | bar: 2008-11-07 to 2008-11-10
7782 | [AppGen]About window is too ugly | Teng, Kevin |  | 3 | bar: 2008-11-07 to 2008-11-10
7737 | [CHN][installation]there is disorder code in installer Description | Li, Yue | 2008-11-07 18:57 | 3 | bar: 2008-11-10 to 2008-11-12
7781 | [CHN] Cannot print COLD document with Text/Image overlay. | Liu, Travis | 2008-11-07 16:17 | 2 | bar: 2008-11-10 to 2008-11-12
7768 | [WX]delete select index from auto index list,even do not select any index, there is no warning message | Li, Yue | 2008-11-11 06:51 | 3 | bar: 2008-11-11 to 2008-11-12
6608 | [Translation][AppGen] User privilege should be translated to "用户权限" not "用户特权"(102) | Liu, Travis | 2008-11-10 13:02 | 3 | bar: 2008-11-11 to 2008-11-12
7475 | [Translation] Copy or Move pages menu and panel are not localized into Chinese. | Liu, Travis | 2008-11-10 15:26 | 2 | bar: 2008-11-11 to 2008-11-12
6610 | [Translation][AppGen] Full text path should be translated to "全文索引路径" not "全文数据库路径" (104). | Liu, Travis | 2008-11-10 15:46 | 3 | bar: 2008-11-11 to 2008-11-12
7530 | [Translation] Error message is not localized into Chinese. | Liu, Travis | 2008-11-10 17:03 | 3 | bar: 2008-11-11 to 2008-11-12
6619 | [Translation][AX] The hint string of "Record management retention status" in IRC viewer is not localized into Chinese. | Liu, Travis | 2008-11-10 17:05 | 3 | bar: 2008-11-11 to 2008-11-14
7476 | [Translation] Reorder page menu are not localized into Chinese. | Liu, Travis | 2008-11-10 17:07 | 2 | bar: 2008-11-11 to 2008-11-12
7752 | [WXJ2] Missing text in WXJ2 installation wizard. | Liu, Travis | 2008-11-10 17:35 | 2 | bar: 2008-11-11 to 2008-11-13
6622 | [Translation][AX] "A document that is under retention administration can not be locked" error message is not localized into Chinese. | Liu, Travis | 2008-11-10 17:38 | 3 | bar: 2008-11-11 to 2008-11-14
7697 | [Installation]Can't use Installer.exe in Vista | Teng, Kevin | 2008-11-10 10:59 | 2 | bar: 2008-11-11 to 2008-11-12
7779 | [XsAdmin]About window is too ugly | Teng, Kevin | 2008-11-10 11:20 | 3 | bar: 2008-11-11 to 2008-11-12
7780 | [AX]About window is too ugly | Teng, Kevin | 2008-11-10 11:20 | 3 | bar: 2008-11-11 to 2008-11-12
7782 | [AppGen]About window is too ugly | Teng, Kevin | 2008-11-10 11:20 | 3 | bar: 2008-11-11 to 2008-11-12
7783 | [ImageCapture]About window is too ugly | Teng, Kevin | 2008-11-10 11:20 | 3 | bar: 2008-11-11 to 2008-11-12
7784 | [UserProfile]About window is too ugly | Teng, Kevin | 2008-11-10 11:20 | 3 | bar: 2008-11-11 to 2008-11-12
6609 | [Translation][AppGen] software retention is not translated well (103) | Teng, Kevin | 2008-11-10 13:01 | 2 | bar: 2008-11-11 to 2008-11-12
6364 | [WX]Query page index hints are not translated | Teng, Kevin | 2008-11-10 14:25 | 2 | bar: 2008-11-11 to 2008-11-12
6365 | [WX]Index hints on index page are not translated | Teng, Kevin | 2008-11-10 14:27 | 2 | bar: 2008-11-11 to 2008-11-12
7804 | [WX]Import a foreign file using Index Image Import, can't download or render that file in WX | Teng, Kevin | 2008-11-10 15:15 | 2 | bar: 2008-11-11 to 2008-11-12
7499 | [Translation][AX]Copy and Move pages need to be translated | Teng, Kevin | 2008-11-10 15:23 | 2 | bar: 2008-11-11 to 2008-11-12
7178 | The font in UserPID table is not correct(106) | Teng, Kevin | 2008-11-10 17:30 | 3 | bar: 2008-11-11 to 2008-11-12
7387 | [WXJ2]Using evaluation license can't login | Teng, Kevin | 2008-11-10 17:33 | 2 | bar: 2008-11-11 to 2008-11-13
7818 | [WXJ2]Import a foreign file using Index Image Import, can't download or render that file in WXj2 | Teng, Kevin | 2008-11-10 17:49 | 2 | bar: 2008-11-11 to 2008-11-13
7827 | [RenderServer]Change the font of COLD form overlay doesn't take effect | Teng, Kevin | 2008-11-11 01:08 | 2 | bar: 2008-11-11 to 2008-11-14
7697 | [Installation]Can't use Installer.exe in Vista | Li, Yue | 2008-11-10 10:59 | 2 | bar: 2008-11-12 to 2008-11-14
7719 | [AX]key reference import wizard has no validation for 'Skip' and 'Load' options | Li, Yue | 2008-11-12 08:33 | 3 | bar: 2008-11-12 to 2008-11-14
7826 | [CHN][AppGen]audit trail has no saved file browser and path | Li, Yue | 2008-11-11 17:15 | 2 | bar: 2008-11-12 to 2008-11-14
7768 | [WX]delete select index from auto index list,even do not select any index, there is no warning message | Li, Yue | 2008-11-11 06:51 | 3 | bar: 2008-11-12 to 2008-11-14
7805 | [WJ2]save index using 'Enter' causes GUI mess up, duplicate tool bar, display window | Li, Yue | 2008-11-11 16:46 | 2 | bar: 2008-11-12 to 2008-11-14
7857 | Using AX Web .Net Wizard will cause Admin crash. | Liu, Travis | 2008-11-11 16:37 | 2 | bar: 2008-11-12 to 2008-11-14
7856 | Evaluation license cannot be recognized in AX Admin. | Liu, Travis | 2008-11-11 16:37 | 2 | bar: 2008-11-12 to 2008-11-14
7741 | [CHN] Rubber stamp does not support Chinese punctuation (full width). | Liu, Travis | 2008-11-11 23:36 | 3 | bar: 2008-11-12 to 2008-11-14
7827 | [RenderServer]Change the font of COLD form overlay doesn't take effect | Teng, Kevin | 2008-11-11 01:08 | 2 | bar: 2008-11-12 to 2008-11-14
7744 | Use other user will not be able to open the document | Teng, Kevin | 2008-11-11 15:28 | 2 | bar: 2008-11-12 to 2008-11-14
7719 | [AX]key reference import wizard has no validation for 'Skip' and 'Load' options | Li, Yue | 2008-11-12 08:33 | 3 | bar: 2008-11-13 to 2008-11-14
7808 | [WXJ2]if add multi page to one document the UI is different from WX | Li, Yue | 2008-11-12 10:32 | 3 | bar: 2008-11-13 to 2008-11-14
7737 | [CHN][installation]there is disorder code in installer Description | Li, Yue | 2008-11-12 11:42 | 3 | bar: 2008-11-13 to 2008-11-14
7880 | [CHN][WX]网页上有错误,if index field name is '日期' not date | Li, Yue | 2008-11-12 17:07 | 2 | bar: 2008-11-13 to 2008-11-14
6299 | [AXadmin]oracle user does not have enough permission according to AppXtenderCoreComponentsAG_5.40.pdf | Li, Yue | 2008-11-13 01:10 | 2 | bar: 2008-11-13 to 2008-11-14
7689 | [WX] The forms that was saved in the demoDB is in ansi text format, and they will be converted to some unreadable code in Chinese (non-Western Language) OS. | Liu, Travis | 2008-11-13 01:04 | 1 | bar: 2008-11-13 to 2008-11-14
6282 | [Documentation][Admin] Need clear explaination for the unicode choice | Liu, Travis | 2008-11-13 01:10 | 3 | bar: 2008-11-13 to 2008-11-14
7741 | [CHN] Rubber stamp does not support Chinese punctuation (full width). | Liu, Travis | 2008-11-13 05:54 | 3 | bar: 2008-11-13 to 2008-11-14
7862 | [DataSorSel] Locate the datasource will cause error | Teng, Kevin | 2008-11-12 10:28 | 1 | bar: 2008-11-13 to 2008-11-14
7815 | [WXJ2]It should have vertical scrollbar in Setting page | Teng, Kevin | 2008-11-12 13:35 | 3 | bar: 2008-11-13 to 2008-11-14
7881 | [AuditTrail]The message of import a document into AX through ODMA is not correct | Teng, Kevin | 2008-11-12 17:26 | 3 | bar: 2008-11-13 to 2008-11-14
6268 | [AX]Text Search for PDF file doesn't work well | Teng, Kevin | 2008-11-12 19:41 | 1 | bar: 2008-11-13 to 2008-11-14
7865 | [AppGen]For demodb apps, Index Image file settings contains duplicated items | Teng, Kevin | 2008-11-12 19:44 | 3 | bar: 2008-11-13 to 2008-11-14
7877 | [AX]Thumnbnail will not be refreshed when opening another document | Teng, Kevin | 2008-11-12 22:40 | 3 | bar: 2008-11-13 to 2008-11-14
7866 | [AX]AX will crash if open and close "copy or move page" | Teng, Kevin | 2008-11-13 02:49 | 2 | bar: 2008-11-13 to 2008-11-14
7425 | [WX]The COLD file exported log is not correct | Teng, Kevin | 2008-11-13 05:17 | 3 | bar: 2008-11-13 to 2008-11-14
6297 | The starting logo is ugly | Teng, Kevin | 2008-11-13 08:52 | 2 | bar: 2008-11-13 to 2008-11-14
7742 | [CHN][AXadmin]demodb is damaged after swith OS user | Li, Yue | 2008-11-13 15:56 | 2 | bar: 2008-11-14
7825 | [WXJ2]data format in autoindex is not correct | Li, Yue | 2008-11-14 09:19 | 2 | bar: 2008-11-14
7178 | The font in UserPID table is not correct(106) | Teng, Kevin | 2008-11-13 22:33 | 3 | bar: 2008-11-14

## Resolved Bronco Bugs
ID | Title | Assigned To | Resolved Date | P | time axis 2008-08-18 to 2008-10-23
6164 | [excel]Open button in Excel AXTO tab does not work | Li, Yue | 2008-07-23 10:59 | 2 | 2008-08-18: Blocked; 2008-08-25: X; 2008-08-26: O
6706 | saved query return original result after replacing non-empty field value with empty value | Li, Yue | 2008-08-16 06:35 | 2 | bar: 2008-08-18 to 2008-08-19
6719 | Word-after click office button "close",could not run query | Li, Yue | 2008-08-15 14:28 | 2 | bar: 2008-08-18 to 2008-08-19
6185 | [Word - DocumentContainerViewWorkItem] Cannot display documents as Xps format. | Liu, Travis | 2008-07-19 05:15 | 1 | bar: 2008-08-18 to 2008-08-19
6211 | [Word] When repeatly open documents as pdf format, word crash. | Liu, Travis | 2008-07-19 04:30 | 2 | bar: 2008-08-18 to 2008-08-19
6132 | [Word]Customized width of panel cannot be remembered into private config file. | Liu, Travis | 2008-07-29 16:40 | 2 | bar: 2008-08-18 to 2008-08-19
6151 | [Word]Business Application cannot be closed. | Liu, Travis | 2008-07-30 05:11 | 1 | bar: 2008-08-18 to 2008-08-19
6153 | [Word]Cannot open AX documents after several times opening. | Liu, Travis | 2008-07-30 05:11 | 2 | bar: 2008-08-18 to 2008-08-19
6695 | Document Element Properties configuration in OutOfBox.xml cause MS Word crash. | Liu, Travis | 2008-08-15 17:47 | 2 | bar: 2008-08-18 to 2008-08-19
6107 | Can not restart Business Application | Teng, Kevin | 2008-07-30 05:11 | 2 | bar: 2008-08-18 to 2008-08-19
6159 | [Word]Search button on AXTO tab doesn't work | Teng, Kevin | 2008-07-21 17:45 | 2 | bar: 2008-08-18 to 2008-08-19
6215 | Results number is not correct if select one filter | Teng, Kevin | 2008-07-16 14:13 | 2 | bar: 2008-08-18 to 2008-08-19
6225 | Set one column SortOrder doesn't work correctly | Teng, Kevin | 2008-07-31 16:57 | 2 | bar: 2008-08-18 to 2008-08-19
6226 | Set 2 columns SortOrder doesn't take any effect | Teng, Kevin | 2008-07-23 10:59 | 2 | bar: 2008-08-18 to 2008-08-19
6227 | Width of first column is not correct | Teng, Kevin | 2008-07-16 14:14 | 2 | bar: 2008-08-18 to 2008-08-19
6722 | Can't perform Search Range | Teng, Kevin | 2008-08-15 15:29 | 2 | bar: 2008-08-18 to 2008-08-19
6723 | List search is not user friendly | Teng, Kevin | 2008-08-15 17:45 | 3 | bar: 2008-08-18 to 2008-08-19
6696 | Double click the title bar will open the first doc | Teng, Kevin | 2008-08-15 18:05 | 3 | bar: 2008-08-18 to 2008-08-19
6701 | Unselected tab in ResultSetConfigDialog is not obviously | Teng, Kevin | 2008-08-15 18:05 | 3 | bar: 2008-08-18 to 2008-08-19
6703 | Sort Type doesn't work | Teng, Kevin | 2008-08-15 18:05 | 2 | bar: 2008-08-18 to 2008-08-19
6704 | Set Filter doesn't work | Teng, Kevin | 2008-08-15 18:05 | 2 | bar: 2008-08-18 to 2008-08-19
6774 | Outlook-the version is not consistent in ExplorerBusinessUseCase config file,some is 1.0,others is 1.0.0.0 | Li, Yue | 2008-08-19 00:07 | 2 | bar: 2008-08-19 to 2008-08-20
6698 | Word-sometimes open Word,there is no Login icon under office button | Li, Yue | 2008-08-19 00:02 | 2 | bar: 2008-08-19 to 2008-08-20
6691 | Word-login workitem is gray | Li, Yue | 2008-08-19 00:13 | 2 | bar: 2008-08-19 to 2008-08-20
6692 | Word-login options can not uncheck "Save Credentials" | Li, Yue | 2008-08-19 04:09 | 2 | bar: 2008-08-19 to 2008-08-20
6671 | Word has two opend ApplicationXtender views pane displayed | Li, Yue | 2008-08-19 04:24 | 1 | bar: 2008-08-19 to 2008-08-20
6700 | Word-open document from AX can select "check out" and "open as read only" same time | Li, Yue | 2008-08-18 22:25 | 2 | bar: 2008-08-19 to 2008-08-20
6721 | Word- generate reference values of HR application, it always throw an exception | Li, Yue | 2008-08-19 09:31 | 2 | bar: 2008-08-19 to 2008-08-20
6764 | Word-show properties will cause Word crash,if the document bin file is not existed | Li, Yue | 2008-08-19 04:35 | 3 | bar: 2008-08-19 to 2008-08-20
6690 | After closing one business application, cannot reopen any business application any more. | Liu, Travis | 2008-08-19 04:20 | 1 | bar: 2008-08-19 to 2008-08-20
6725 | Automatically login to this store check box is not disabled after business application loaded. | Liu, Travis | 2008-08-19 04:27 | 2 | bar: 2008-08-19 to 2008-08-20
6132 | [Word]Customized width of panel cannot be remembered into private config file. | Liu, Travis | 2008-08-19 | 2 | bar: 2008-08-19 to 2008-08-20
6107 | Can not restart Business Application | Teng, Kevin | 2008-08-18 22:57 | 2 | bar: 2008-08-19 to 2008-08-20
6724 | Save Credentials and "Automatically login to this store" doesn't work | Teng, Kevin | 2008-08-18 22:49 | 2 | bar: 2008-08-19 to 2008-08-20
6745 | No thumbnail displayed in Thumbnail workitem | Teng, Kevin | 2008-08-19 09:27 | 2 | bar: 2008-08-19 to 2008-08-20
6813 | Word-two login have different configuration | Li, Yue | 2008-08-19 20:52 | 2 | bar: 2008-08-21 to 2008-08-22
6779 | Outlook-loan number is lost on query result set | Li, Yue | 2008-08-19 17:36 | 2 | bar: 2008-08-21 to 2008-08-22
6702 | Word-open document from AX,no publish to AX | Li, Yue | 2008-08-20 05:32 | 2 | bar: 2008-08-21 to 2008-08-22
6773 | Outlook-unload Outlook Addin could not remove all the menu items, folders etc | Li, Yue | 2008-08-19 23:17 | 2 | bar: 2008-08-21 to 2008-08-22
6806 | Outlook-install outlook vsto file failed | Li, Yue | 2008-08-19 18:05 | 1 | bar: 2008-08-21 to 2008-08-22
6781 | Title ODMA property is not correctly. | Liu, Travis | 2008-08-20 00:30 | 2 | bar: 2008-08-20 to 2008-08-21
6699 | Result set work item is still workable after log out. | Liu, Travis | 2008-08-19 14:02 | 2 | bar: 2008-08-20 to 2008-08-21
6703 | Sort Type doesn't work | Teng, Kevin | 2008-08-19 17:51 | 2 | bar: 2008-08-20 to 2008-08-21
6778 | Change Field Width doesn't work | Teng, Kevin | 2008-08-19 17:51 | 2 | bar: 2008-08-20 to 2008-08-21
6809 | Save Credentials checkbox will be automatically checked when start business workitem the second time | Teng, Kevin | 2008-08-19 21:06 | 2 | bar: 2008-08-20 to 2008-08-21
6819 | Cannot view&render any document any more after viewing a HTML document. | Liu, Travis | 2008-08-21 04:38 | 2 | bar: 2008-08-21 to 2008-08-22
6814 | Full Text Search text box is still shown in the Query tab after unchecking "Enable Full Text" check box and re-login. | Liu, Travis | 2008-08-20 11:35 | 2 | bar: 2008-08-21 to 2008-08-22
6185 | [Word - DocumentContainerViewWorkItem] Cannot display documents as Xps format. | Liu, Travis | 2008-08-20 19:47 | 1 | bar: 2008-08-21 to 2008-08-22
6823 | Failed to execute query will occur when perform search | Teng, Kevin | 2008-08-21 01:09 | 1 | bar: 2008-08-21 to 2008-08-22
6829 | Change query name and save, the previous query should be removed | Teng, Kevin | 2008-08-21 07:10 | 3 | bar: 2008-08-21 to 2008-08-25
6828 | Save query again will throw an exception | Teng, Kevin | 2008-08-21 07:02 | 2 | bar: 2008-08-21 to 2008-08-25
6812 | Delete button in field box doesn't work | Teng, Kevin | 2008-08-20 15:37 | 2 | bar: 2008-08-21 to 2008-08-22
6857 | Outlook-logout always pop up warning message | Li, Yue | 2008-08-21 21:58 | 2 | bar: 2008-08-22 to 2008-08-25
6859 | Outlook-login,logout all icon is missed | Li, Yue | 2008-08-21 21:54 | 2 | bar: 2008-08-22 to 2008-08-25
6777 | Outlook-Inspector Close Error message pop up, after new email then click "X" to close it | Li, Yue | 2008-08-21 18:19 | 2 | bar: 2008-08-22 to 2008-08-25
6850 | Integer type properties still contain a underline after save. | Liu, Travis | 2008-08-22 03:40 | 3 | bar: 2008-08-22 to 2008-08-25
6854 | Zoom bar of elements' thumbnails do not work. | Liu, Travis | 2008-08-22 03:16 | 2 | bar: 2008-08-22 to 2008-08-25
6860 | During using AXO in Word, the frequency of Word crash is higher than expectation. | Liu, Travis | 2008-08-21 20:47 | 2 | bar: 2008-08-22 to 2008-08-25
6821 | It should not save to configuration if don't check "Save customized configuration" checkbox | Teng, Kevin | 2008-08-21 19:05 | 2 | bar: 2008-08-22 to 2008-08-25
6851 | Between using Wildcard search is not correct | Teng, Kevin | 2008-08-22 06:18 | 3 | bar: 2008-08-22 to 2008-08-25
6853 | The label of Search Expression in Bronco is different with AX | Teng, Kevin | 2008-08-22 05:38 | 3 | bar: 2008-08-22 to 2008-08-25
6861 | Save Query will crash | Teng, Kevin | 2008-08-21 21:59 | 1 | bar: 2008-08-22 to 2008-08-25
6780 | Could only add 1 Filter | Teng, Kevin | 2008-08-21 18:19 | 2 | bar: 2008-08-22 to 2008-08-25
6744 | Can't save modification in Properties window | Teng, Kevin | 2008-08-22 03:07 | 2 | bar: 2008-08-22 to 2008-08-25
6857 | Outlook-logout always pop up warning message | Li, Yue | 2008-08-22 20:59 | 2 | bar: 2008-08-25 to 2008-08-26
6877 | Outlook-close Login window need twice click "Close" button | Li, Yue | 2008-08-23 01:10 | 3 | bar: 2008-08-25 to 2008-08-26
6883 | Outlook-two stores,after login one store the login button is gray | Li, Yue | 2008-08-23 01:17 | 2 | bar: 2008-08-25 to 2008-08-26
6874 | There is no reaction in most situation when try to render document in "NewWindow". | Liu, Travis | 2008-08-23 01:49 | 2 | bar: 2008-08-25 to 2008-08-26
6876 | CreatedBy property is editable. | Liu, Travis | 2008-08-23 05:44 | 2 | bar: 2008-08-25 to 2008-08-26
6872 | Word crash if switch results quickly | Teng, Kevin | 2008-08-22 22:22 | 1 | bar: 2008-08-25 to 2008-08-26
6720 | The tab is not obvious in drop down menu of the search index | Teng, Kevin | 2008-08-23 00:51 | 3 | bar: 2008-08-25 to 2008-08-26
6701 | Unselected tab in ResultSetConfigDialog is not obviously | Teng, Kevin | 2008-08-23 00:57 | 3 | bar: 2008-08-25 to 2008-08-26
6164 | [excel]Open button in Excel AXTO tab does not work | Li, Yue | 2008-08-26 02:53 | 2 | bar: 2008-08-26 to 2008-08-27
6894 | Customize button does not work. | Liu, Travis | 2008-08-25 22:50 | 1 | bar: 2008-08-26 to 2008-08-27
6897 | Error message pop up when publishing new element. | Liu, Travis | 2008-08-26 03:55 | 2 | bar: 2008-08-26 to 2008-08-27
6898 | New Element Version is added to the wrong page. | Liu, Travis | 2008-08-26 01:29 | 1 | bar: 2008-08-26 to 2008-08-27
6872 | Word crash if switch results quickly | Teng, Kevin | 2008-08-26 02:24 | 1 | bar: 2008-08-26 to 2008-08-27
6899 | Full Text search using Expression doesn't work | Teng, Kevin | 2008-08-25 22:04 | 2 | bar: 2008-08-26 to 2008-08-27
6849 | Login as second user will still use the saved query by first user | Teng, Kevin | 2008-08-25 22:22 | 2 | bar: 2008-08-26 to 2008-08-27
6875 | Search using CreatedBy doesn't work | Teng, Kevin | 2008-08-25 23:28 | 2 | bar: 2008-08-26 to 2008-08-27
6891 | Can't perform CAQ query | Teng, Kevin | 2008-08-25 22:23 | 2 | bar: 2008-08-26 to 2008-08-27
6892 | Only "Simple" works in LayourStyle | Teng, Kevin | 2008-08-26 09:50 | 3 | bar: 2008-08-26 to 2008-08-27
6873 | There is no total result number | Teng, Kevin | 2008-08-25 15:04 | 2 | bar: 2008-08-26 to 2008-08-27
6895 | Outlook-attach one file with page range then open it, only open the attached | Li, Yue | 2008-08-26 23:17 | 2 | bar: 2008-08-27 to 2008-08-28
6917 | Outlook-upload to ax configuration can not save Upload item message format | Li, Yue | 2008-08-27 00:27 | 2 | bar: 2008-08-27 to 2008-08-28
6919 | Outlook-add new upload configuration to folder is failed | Li, Yue | 2008-08-27 00:27 | 2 | bar: 2008-08-27 to 2008-08-28
6920 | Outlook-could not delete multi record at the same time,Upload to ApplicationXtender and ApplicationXtender Browsing | Li, Yue | 2008-08-26 21:43 | 3 | bar: 2008-08-27 to 2008-08-28
6916 | Need to click <Save> button twice to save the modification of properties. | Liu, Travis | 2008-08-27 05:53 | 2 | bar: 2008-08-27 to 2008-08-28
6908 | Full Text Search has cache | Teng, Kevin | 2008-08-26 19:56 | 2 | bar: 2008-08-27 to 2008-08-28
6878 | Can't login AXO when using Evaluation License Server | Teng, Kevin | 2008-08-27 09:11 | 2 | bar: 2008-08-27 to 2008-08-29
6953 | Excel-open from ax will cause Business Applications lost 2 menu items | Li, Yue | 2008-08-28 00:11 | 1 | bar: 2008-08-28 to 2008-08-29
6895 | Outlook-attach one file with page range then open it, only open the attached | Li, Yue | 2008-08-26 23:17 | 2 | bar: 2008-08-28 to 2008-08-29
6922 | Outlook-export email to ax fail | Li, Yue | 2008-08-27 21:49 | 1 | bar: 2008-08-28 to 2008-08-29
6949 | Outlook-move to AX then cancel,but email is deleted | Li, Yue | 2008-08-28 04:26 | 2 | bar: 2008-08-28 to 2008-08-29
6705 | Word-checked out document can be checked out again in AXTO | Li, Yue | 2008-08-28 00:14 | 2 | bar: 2008-08-28 to 2008-08-29
6897 | Error message pop up when publishing new element. | Liu, Travis | 2008-08-28 06:28 | 2 | bar: 2008-08-28 to 2008-08-29
6950 | [PowerPoint] Cannot open PowerPoint type document. | Liu, Travis | 2008-08-28 02:12 | 2 | bar: 2008-08-28 to 2008-08-29
6909 | Query does not respect OR with Full Text when field values are empty | Teng, Kevin | 2008-08-28 01:40 | 2 | bar: 2008-08-28 to 2008-08-29
6873 | There is no total result number | Teng, Kevin | 2008-08-27 18:34 | 3 | bar: 2008-08-28 to 2008-08-29
6921 | The result set view should be in the top of the workspace | Teng, Kevin | 2008-08-27 18:34 | 3 | bar: 2008-08-28 to 2008-08-29
6895 | Outlook-attach one file with page range then open it, only open the attached | Li, Yue | 2008-08-28 21:55 | 2 | bar: 2008-08-29 to 2008-09-01
6966 | Outlook-batch email auto upload to ax is failed | Li, Yue | 2008-08-29 01:37 | 1 | bar: 2008-08-29 to 2008-09-01
6879 | Outlook-browsing set thinView=false, open document is not IRC | Li, Yue | 2008-08-28 23:51 | 2 | bar: 2008-08-29 to 2008-09-01
6881 | Outlook browsing-set two stores,only the saved query in the store first logged into can be viewed correctly | Li, Yue | 2008-08-29 00:35 | 1 | bar: 2008-08-29 to 2008-09-01
6951 | [Word/ PowerPoint/ Excel] "CreateBy", "CreatedDate", "ModifiedBy", "ModifiedDate" are editable when publishing document. | Liu, Travis | 2008-08-28 14:36 | 2 | bar: 2008-08-29 to 2008-09-01
6950 | [PowerPoint] Cannot open PowerPoint type document. | Liu, Travis | 2008-08-28 22:03 | 2 | bar: 2008-08-29 to 2008-09-01
6882 | Error message pop up when open document in WebAccessMode(IRC mode). | Liu, Travis | 2008-08-29 04:41 | 3 | bar: 2008-08-29 to 2008-09-01
6948 | [PowerPoint - DocumentContainerViewWorkItem] Cannot display documents as Xps format. | Liu, Travis | 2008-08-28 22:40 | 1 | bar: 2008-08-29 to 2008-09-01
6945 | Some text in Customization page can't be shown wholly | Teng, Kevin | 2008-08-28 19:33 | 2 | bar: 2008-08-29 to 2008-09-01
6878 | Can't login AXO when using Evaluation License Server | Teng, Kevin | 2008-08-29 05:15 | 2 | bar: 2008-08-29 to 2008-09-01
6875 | Search using CreatedBy doesn't work | Teng, Kevin | 2008-08-29 02:33 | 2 | bar: 2008-08-29 to 2008-09-01
6952 | Modify Top doesn't take effect | Teng, Kevin | 2008-08-28 19:02 | 2 | bar: 2008-08-29 to 2008-09-01
6988 | Outlook-open document from result set fail | Li, Yue | 2008-08-29 19:38 | 2 | bar: 2008-09-01 to 2008-09-02
6879 | Outlook-browsing set thinView=false, open document is not IRC | Li, Yue | 2008-08-28 23:51 | 2 | bar: 2008-09-01 to 2008-09-02
6983 | Outlook-ApplicationXtender Browsing set up UI, add query has gray block | Li, Yue | 2008-08-29 21:15 | 3 | bar: 2008-09-01 to 2008-09-02
6984 | Outlook-browsing add query, there is no validation between Content Type and Saved Query | Li, Yue | 2008-08-29 21:11 | 2 | bar: 2008-09-01 to 2008-09-02
6950 | [PowerPoint] Cannot open PowerPoint type document. | Liu, Travis | 2008-08-30 01:38 | 2 | bar: 2008-09-01 to 2008-09-02
6948 | [PowerPoint - DocumentContainerViewWorkItem] Cannot display documents as Xps format. | Liu, Travis | 2008-08-28 22:40 | 1 | bar: 2008-09-01 to 2008-09-02
6882 | Error message pop up when open document in WebAccessMode(IRC mode). | Liu, Travis | 2008-08-29 04:41 | 3 | bar: 2008-09-01 to 2008-09-02
6978 | Check in doesn't work | Teng, Kevin | 2008-08-30 01:16 | 2 | bar: 2008-09-01 to 2008-09-02
6980 | The Check out checkbox should be disabled if the document is Final revision | Teng, Kevin | 2008-08-29 17:21 | 2 | bar: 2008-09-01 to 2008-09-02
6981 | It will cause exception when New document revision for a final revision document | Teng, Kevin | 2008-08-30 01:16 | 2 | bar: 2008-09-01 to 2008-09-02
6987 | New Document in AppXtender Ribbon panel should not perform same action as Publish to AX | Teng, Kevin | 2008-08-29 20:54 | 2 | bar: 2008-09-01 to 2008-09-02
6989 | View some documents for the first time will cause error | Teng, Kevin | 2008-08-29 19:39 | 2 | bar: 2008-09-01 to 2008-09-02
6990 | Using updated WX, New document revision will hang | Teng, Kevin | 2008-08-30 04:22 | 2 | bar: 2008-09-01 to 2008-09-02
6991 | Replace confirm dialog box always popup when new document | Teng, Kevin | 2008-08-30 02:29 | 2 | bar: 2008-09-01 to 2008-09-02
6878 | Can't login AXO when using Evaluation License Server | Teng, Kevin | 2008-08-30 06:50 | 2 | bar: 2008-09-01 to 2008-09-02
6954 | [Word]Can't login after automatically logout | Teng, Kevin | 2008-08-29 19:13 | 3 | bar: 2008-09-01 to 2008-09-02
7023 | Upload a HTML file is recognized as unknown file in AX. | Li, Yue | 2008-09-02 22:25 | 2 | bar: 2008-09-03 to 2008-09-04
6966 | Outlook-batch email auto upload to ax is failed | Li, Yue | 2008-09-03 00:31 | 1 | bar: 2008-09-03 to 2008-09-04
7019 | Outlook-email export to ax using Item's default, it becomes unreadable code in AX | Li, Yue | 2008-09-02 15:56 | 1 | bar: 2008-09-03 to 2008-09-04
7020 | Outlook-email export to ax using 3 Upload item message format:Text(*.txt),HTML(*.htm),Rich Text(*.rtf) fail | Li, Yue | 2008-09-02 15:56 | 2 | bar: 2008-09-03 to 2008-09-04
6983 | Outlook-ApplicationXtender Browsing set up UI, add query has gray block | Li, Yue | 2008-09-03 05:14 | 3 | bar: 2008-09-03 to 2008-09-04
7012 | Multipleindex navigation bar in document properties panel does not work. | Liu, Travis | 2008-09-03 01:55 | 2 | bar: 2008-09-03 to 2008-09-04
7010 | <Viewer> element do not work for WebAccessMode. | Liu, Travis | 2008-09-02 23:07 | 2 | bar: 2008-09-03 to 2008-09-04
7014 | Open word type document in powerpoint, error message is not accurate. | Liu, Travis | 2008-09-03 02:49 | 3 | bar: 2008-09-03 to 2008-09-04
7015 | New revision should be for a document instead of a page | Teng, Kevin | 2008-09-02 21:39 | 2 | bar: 2008-09-03 to 2008-09-04
7017 | In query, hard to double click an app | Teng, Kevin | 2008-09-02 16:06 | 3 | bar: 2008-09-03 to 2008-09-04
7018 | New Revision button in AX Ribbon tab is always disabled | Teng, Kevin | 2008-09-03 02:56 | 3 | bar: 2008-09-03 to 2008-09-04
7021 | Open document will make Word crash | Teng, Kevin | 2008-09-02 16:02 | 1 | bar: 2008-09-03 to 2008-09-04
7022 | Show property will make Word crash | Teng, Kevin | 2008-09-02 15:55 | 1 | bar: 2008-09-03 to 2008-09-04
6878 | Can't login AXO when using Evaluation License Server | Teng, Kevin | 2008-09-03 03:58 | 2 | bar: 2008-09-03 to 2008-09-04
6981 | It will cause exception when New document revision for a final revision document | Teng, Kevin | 2008-09-02 23:36 | 2 | bar: 2008-09-03 to 2008-09-04
6982 | Numeric field value that bigger than integer maximum validating on server but not on client | Teng, Kevin | 2008-09-03 02:39 | 3 | bar: 2008-09-03 to 2008-09-04
6990 | Using updated WX, New document revision will hang | Teng, Kevin | 2008-09-03 02:17 | 3 | bar: 2008-09-03 to 2008-09-04
6923 | Outlook-no validation for attached page range | Li, Yue | 2008-09-04 02:28 | 3 | bar: 2008-09-04 to 2008-09-05
7031 | Outlook-new email do query then close it,there is error message | Li, Yue | 2008-09-03 19:04 | 2 | bar: 2008-09-04 to 2008-09-05
6983 | Outlook-ApplicationXtender Browsing set up UI, add query has gray block | Li, Yue | 2008-09-04 01:10 | 3 | bar: 2008-09-04 to 2008-09-05
6132 | [Word]Customized width of panel cannot be remembered into private config file. | Liu, Travis | 2008-09-04 00:01 | 3 | bar: 2008-09-04 to 2008-09-05
7033 | Icon for the multipleindex navigation bar is not correct. | Liu, Travis | 2008-09-03 18:18 | 3 | bar: 2008-09-04 to 2008-09-05
6981 | It will cause exception when New document revision for a final revision document | Teng, Kevin | 2008-09-03 21:10 | 2 | bar: 2008-09-04 to 2008-09-05
7032 | First time New revision won't work | Teng, Kevin | 2008-09-03 21:24 | 2 | bar: 2008-09-04 to 2008-09-05
7050 | Outlook-browsing content is lost | Li, Yue | 2008-09-04 22:51 | 2 | bar: 2008-09-05 to 2008-09-08
7049 | Sorting for Hire date is not correct | Teng, Kevin | 2008-09-04 23:06 | 2 | bar: 2008-09-05 to 2008-09-08
6879 | Outlook-browsing set thinView=false, open document is not IRC | Li, Yue | 2008-09-06 00:11 | 2 | bar: 2008-09-08 to 2008-09-10
6882 | Error message pop up when open document in WebAccessMode(IRC mode). | Liu, Travis | 2008-09-06 00:08 | 2 | bar: 2008-09-08 to 2008-09-10
7066 | After viewing document in workspace, there is always a "Please wait a moment..." message there, and word has no reaction at all. | Liu, Travis | 2008-09-05 18:23 | 1 | bar: 2008-09-08 to 2008-09-10
7067 | Click Search button in Publish to AX dialogue doesn't work | Teng, Kevin | 2008-09-05 18:30 | 1 | bar: 2008-09-08 to 2008-09-09
7079 | Do "Open from AX" operation, when the session is time out, there is no error message when clicking <search> button. | Liu, Travis | 2008-09-08 22:06 | 2 | bar: 2008-09-09 to 2008-09-10
7094 | Outlook-attach rendering format is XPS can not work for msg/oft/docx/pdf file | Li, Yue | 2008-09-10 05:06 | 3 | bar: 2008-09-10 to 2008-09-11
7095 | Outlook-render file name is same | Li, Yue | 2008-09-10 00:22 | 2 | bar: 2008-09-10 to 2008-09-11
6879 | Outlook-browsing set thinView=false, open document is not IRC | Li, Yue | 2008-09-10 00:57 | 2 | bar: 2008-09-10 to 2008-09-11
7096 | Powerpoint -- Open second ppt, click New document doesn't work | Teng, Kevin | 2008-09-10 03:03 | 2 | bar: 2008-09-10 to 2008-09-11
7106 | Outlook-copy email to ax using attachonly, xps and docx file can not be read in AX | Li, Yue | 2008-09-10 | 3 | bar: 2008-09-11 to 2008-09-12
7105 | Word-open word then load basic content management, the default task pane is not displayed at left area | Li, Yue | 2008-09-10 | 2 | bar: 2008-09-11 to 2008-09-12
7095 | Outlook-render file name is same | Li, Yue | 2008-09-10 | 2 | bar: 2008-09-11 to 2008-09-12
7104 | Open Document will cause error | Teng, Kevin | 2008-09-10 22:12 | 1 | bar: 2008-09-11 to 2008-09-12
7108 | It will popup an error when check out a document | Teng, Kevin | 2008-09-10 22:18 | 2 | bar: 2008-09-11 to 2008-09-12
7109 | Cancel check out in property work item, the AX ribbon state will not change | Teng, Kevin | 2008-09-11 05:51 | 3 | bar: 2008-09-11 to 2008-09-12
7110 | Locked won't be checked in properties tab if the document is locked | Teng, Kevin | 2008-09-10 19:14 | 2 | bar: 2008-09-11 to 2008-09-12
7124 | Word-Search New Query in Queries does not work | Li, Yue | 2008-09-12 16:47 | 2 | bar: 2008-09-16 to 2008-09-17
7141 | Query-Customize this Query View Work Item window has no minimize,maximize, close buttons | Li, Yue | 2008-09-12 21:31 | 3 | bar: 2008-09-16 to 2008-09-17
7142 | Word-open from AX, query result shows contenttype name+index field name, but CAQ query result shows CAQ name index field name | Li, Yue | 2008-09-16 03:58 | 3 | bar: 2008-09-16 to 2008-09-17
7143 | Word-if click one Cross Appliaction Query is not displayed, click the others are not displayed ,even they can be displayed originally | Li, Yue | 2008-09-12 16:59 | 2 | bar: 2008-09-16 to 2008-09-17
7121 | If the configurated datasource (Store) does not existed, there is no reaction when clicking <Login> button. | Liu, Travis | 2008-09-11 23:41 | 3 | bar: 2008-09-16 to 2008-09-17
7185 | If show properties menu is on the above of word status bar, it will not work | Teng, Kevin | 2008-09-18 00:35 | 3 | bar: 2008-09-18 to 2008-09-19
7186 | Word will crash several steps | Teng, Kevin | 2008-09-18 00:10 | 2 | bar: 2008-09-18 to 2008-09-19
7191 | Outlook-add Upload to ApplicationXtender configuration, even Cancel it will create an blank one,only can edit or delete, could not add new one | Li, Yue | 2008-09-18 22:31 | 2 | bar: 2008-09-19 to 2008-09-20
6978 | Check in doesn't work | Teng, Kevin | 2008-09-18 21:37 | 2 | bar: 2008-09-19 to 2008-09-20
6978 | Check in doesn't work | Teng, Kevin | 2008-09-18 21:37 | 2 | bar: 2008-09-20 to 2008-09-21
7215 | In Excel, Click New Document in Read Only mode will not work | Teng, Kevin | 2008-09-23 03:46 | 2 | bar: 2008-09-20 to 2008-09-21
7218 | Word-click Views icon in Elements of Document Properties, it will not switch between Icons,list,details,titles, thumbnails | Li, Yue | 2008-10-09 09:21 | 3
7235 | Full text search won't display if open Word again | Teng, Kevin | 2008-10-08 11:13 | 3

## New CM55 Bugs
ID | Title | Created By | Created Date | Activated By | Activated Date | Priority
7741 | [CHN] Rubber stamp does not support Chinese punctuation (full width). | Liu, Travis | 2008-10-31 17:02 | Young, Lawrence | 2008-11-13 05:50 | 3
7911 | [WX] Form overlay cannot be rendered correctly in thin client. | Liu, Travis | 2008-11-13 10:20 | Liu, Travis | 2008-11-13 10:20 | 2
7758 | [FullText]Can't perform Expression Search | Teng, Kevin | 2008-11-03 17:04 | Teng, Kevin | 2008-11-13 09:42 | 2